## Project Timeline
Final Project Timeline
PROJECT TITLE |  | Customer Churn Machine Learning Model |  | COMPANY NAME
PROJECT MEMBERS |  | Molly Gac, Tazia Jones, Sheila LaRoue, Rhi Sehl |  | DATE | [6 empty] | 2023-05-27
PHASE |  |  | DETAILS | WEEK 1 | [7 empty] | WEEK 2 | [6 empty] | WEEK 3
|  |  |  | MAY |  |  |  |  | JUNE
|  |  |  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Project Conception and Initiation |  | Molly | MAY 27: Proposal & determine datasets; JUNE 12: PRESENTATION
Tazia
Sheila
Rhi: Create timeline and set up organizational tools
2 | Data Fetching / API Integration |  | Molly | MAY 29: Fetch all needed data and add to GitHub
Tazia
Sheila
Rhi
3 | Data Analysis |  | Molly | MAY 31: Clean data and do initial analysis
Tazia
Sheila
Rhi
4 | Building ML Model |  | Molly | JUNE 1: Create Machine Learning Model
Tazia
Sheila
Rhi
5 | Testing |  | Molly | JUNE 3: Test model and fine-tune parameters
Tazia
Sheila
Rhi
5 | Creating Documentation |  | Molly | JUNE 1: Create documentation (ReadMe, pseudocode framework)
Tazia
Sheila
Rhi
5 | Creating Presentation |  | Molly | MAY 29: Rough-outline
|  |  | Tazia | JUNE 2: Finish presentation
|  |  | Sheila | JUNE 6: Presentation Practice & Final Touches
Rhi

## Checklist
Project Conception and Initiation |  | Data Fetching / API Integration |  | Data Cleaning & Analysis |  | Building ML Model |  | Testing |  | Creating Documentation |  | Creating Presentation
TRUE | Create timeline | TRUE | Locate dataset(s) | TRUE | Merge two datasets | FALSE | Determine list of what models make sense | FALSE | test at least two models | FALSE | analytical report ('for company') | FALSE | canva for class (linked with tableau)
TRUE | Create proposal | TRUE | Load data into notebook --COLAB-- | TRUE | Remove extraneous columns | FALSE | Choose ML model(s): regression / NN | FALSE | show model optimization | FALSE | Create ReadMe | FALSE | scripting
TRUE | Set up Repo | FALSE |  | TRUE | Remove nulls | FALSE | --train-test-split | FALSE |  | FALSE | Clean psuedocode | FALSE
TRUE | Set up all Colab notebooks | FALSE |  | FALSE | Preliminary analysis | FALSE |  | FALSE |  | FALSE | Full graphs / story in Tableau | FALSE
TRUE | add everyone to all colab/repo/canva | FALSE |  | FALSE | Create basic charts | FALSE | Logistic Regression | FALSE |  | FALSE | Download all colab notebooks and add to github | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE | Naive Bayes | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE | **clarify what the two different colors on the probability charts are | FALSE | Decision Tree | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE | Support Vector Machine | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE | Random Forest? | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE

## Rubric
TRUE | Python script initializes, trains and evaluates a model | 10
TRUE | The data is cleaned, normalized, and standardized prior to modeling | 5
TRUE | The model utilizes data retrieved from SQL or Spark | 5
FALSE | The model demonstrates meaningful predictive power at least 75% classification accuracy or .80 R-squared | 5
FALSE | The model optimization and evaluation process showing iterative changes made to the model and resulting changes in model performance is documented in either a CSV/Excel table or in the Python script itself | 15
FALSE | Overall model performance is printed or displayed at the end of the script | 10
FALSE | GitHub repository is free of unnecessary files and folders and has an appropriate .gitignore in use | 10
FALSE | The README is customized as a polished presentation of the content of the project | 15
FALSE | Presentation: all group members speak | 5
FALSE | Presentation: content, transitions, and conclusions flow smoothly within any time restrictions | 5
FALSE | Presentation: the content is relevant to the project | 10
FALSE | Presentation: maintains audience interest | 5